## WBS Outline & Diagram
WBS OUTLINE & DIAGRAM
PROJECT TITLE | uThukela Hospital Network Infrastructure | COMPANY | ProTech Team
PROJECT MGR | Maduvha Mavhusha | DATE | 2024-08-20
| OUTLINE |  |  | OUTLINE
|  | Mpho Raletjena |  |  | Masana Mavhusha
| 1 | Infrastructure Assessment |  | 7 | Prepare Installatioin Site
| 1.1 | Conduct a site survey to evaluate existing infrastructure at the hospital. |  | 7.1 | Identify and clear the physical space required for the installation of network hardware.
| 1.2 | Identify gaps in current network capabilities and security measures. |  | 7.2 | Ensure that the installation site has adequate power supply and cooling systems.
| 1.3 | Document findings and prepare an assessment report. |  | 7.3 | Set up temporary infrastructure or network redundancies to avoid disruption during installation.
| 2 | Project Charter Finalization |  | 8 | Install Network Infrastructure
| 2.1 | Draft the project charter based on initial assessments and requirements. |  | 8.1 | Deploy and configure network hardware (e.g., routers, switches, servers) on-site.
| 2.2 | Review the draft charter with key stakeholders for feedback. |  | 8.2 | Connect the hospital’s existing systems to the new network infrastructure.
| 2.3 | Finalize and obtain approval for the project charter from all stakeholders. |  | 8.3 | Perform initial configuration of the network settings and parameters.
| 3 | Risk assessment & mitigation planning |  | 9 | Implement security measures & conduct initial testing
| 3.1 | Identify potential risks related to the project’s scope, timeline, and resources. |  | 9.1 | Install and configure firewalls and antivirus software. Set up encryption protocols for data transmission and storage.
| 3.2 | Analyze the likelihood and impact of identified risks. |  | 9.2 | Conduct security tests, including penetration testing, to ensure the network is secure. Run diagnostic tests to verify network connectivity and performance.
| 3.3 | Develop a risk mitigation plan, including contingency strategies. |  | 9.3 | Identify and troubleshoot any issues or bottlenecks in the network setup. Document test results and perform any necessary adjustments.
|  | Chuene Tsholo |  |  | Ntsako Majozi
| 4 | Risk assessment & mitigation planning |  | 10 | Develop & conduct training for ICT staff
| 4.1 | Create a detailed network architecture diagram, including hardware and software components. |  | 10.1 | Create user manuals and troubleshooting guides for the new network infrastructure. Develop training presentations and hands-on activities for ICT support staff.
| 4.2 | Define technical specifications for the network equipment to be used. |  | 10.2 | Schedule training sessions with the ICT support team. Deliver training on network installation, maintenance, and troubleshooting.
| 4.3 | Review and validate the network design with technical stakeholders. |  | 10.3 | Assess the ICT team’s understanding and provide additional support as needed.
| 5 | Identify & procure hardware/software |  | 11 | Final testing & quality assurance
| 5.1 | Research and shortlist potential vendors for hardware and software. |  | 11.1 | Conduct a comprehensive test of the entire network, including security measures.
| 5.2 | Select and finalize the list of hardware and software to be procured. |  | 11.2 | Verify that all components are functioning as expected and meet the project requirements.
| 5.3 | Prepare and issue purchase orders to selected vendors. |  | 11.3 | Document the results of final testing and address any remaining issues.
| 6 | Develop Security Framework |  | 12 | Handover to Hospital management
| 6.1 | Identify key security requirements based on hospital needs and regulations. |  | 12.1 | Conduct a formal handover meeting with hospital management and ICT staff.
| 6.2 | Design a security architecture, including firewalls, encryption, and antivirus. |  | 12.2 | Transfer all project documentation and provide final training or support as needed.
| 6.3 | Develop security policies and procedures to be implemented alongside the network. |  | 12.3 | Establish a post-implementation support plan and schedule a follow-up review.
uThukela Hospital Network Infrastructure
Mpho Raletjena
Infrastructure Assessment
Project Charter finalization
Risk assessment & mitigation planning
Chuene Tsholo
Design Network infrastructure model
Identify & procure hardware/software
Develop security framework
Masana Mavhusha
prepare Installation site
Install network infrastructure
Implement security measures & conduct initial testing
Ntsako Majozi
Develop & conduct training for ICT staff
Final testing & quality assurance
Handover to Hospital management